## Executive Summary
Metric | Value
Total Documents Analyzed | 29
Document Groups | 12
Total Characters | 150,803
Version Numbers Found | 6 (v1.0 to v3.1)
Contradictions Identified | 26
├─ CRITICAL Severity | 4
├─ HIGH Severity | 9
├─ MEDIUM Severity | 10
└─ LOW Severity | 3
Ambiguities Identified | 12
├─ Development Blockers | 8
├─ Medium Priority | 3
└─ Low Priority | 1
Decisions Required | 12
├─ CRITICAL Priority | 4
├─ HIGH Priority | 5
└─ MEDIUM Priority | 3
Current Documents | 29
Proposed Consolidated Documents | 9
Document Reduction | 69% reduction
Estimated Reorganization Time | 13-22 days
Key Recommendation | Create 00_MASTER_DECISIONS.md as single source of truth before any development

## Contradictions
Category | Issue | Source_1 | Value_1 | Source_2 | Value_2 | Severity | Impact
Timeline | Launch Date Conflict | 01.2_ROADMAP_AND_RISK | November 8, 2025 | 01.4_MVP_MASTER_PLAN_SUMMARY | November 29, 2025 | CRITICAL | 21-day discrepancy in launch date across strategic documents
Business Model | Vendor Tier Structure | 05.0_VENDOR_WORKFLOWS | Free Directory + Basic + Pro tiers | 01.1_BUSINESS_PLAN | Transaction commission + Featured slots + "potential subscription" | MEDIUM | Tier structure not clearly defined in business plan vs implementation
Pricing | Featured Slot Pricing | 01.1_BUSINESS_PLAN | $20/month for featured slots | Technical implementation | Queue-based system with Stripe integration (pricing not specified) | MEDIUM | Featured slot pricing model needs clarification in technical docs
Architecture | Directory vs Marketplace Model | 01.1_BUSINESS_PLAN | Described as "digital marketplace" with transaction focus | 05.0_VENDOR_WORKFLOWS & 03.0_TECHNICAL_OVERVIEW | Hybrid Directory–Marketplace architecture (v2.1) | HIGH | Core product positioning unclear - is it primarily directory or marketplace?
Architecture | User Type Definitions | 03.3_SCHEMA_REFERENCE | Users: business_owner OR customer (strict separation) | 05.0_VENDOR_WORKFLOWS | Same business can be in Directory AND Marketplace | MEDIUM | Database schema may not support dual-mode business accounts
Business Logic | Product Upload Limits | 05.0_VENDOR_WORKFLOWS | Free Directory: unlimited listings, Basic: 10 products, Pro: 50 products | 01.1_BUSINESS_PLAN | No mention of product limits or tier restrictions | MEDIUM | Product limit enforcement not defined in business strategy
Operations | Refund Processing Responsibility | 06.4_FOUNDER_OPERATIONS | Vendors responsible for refunds, Suburbmates does NOT process refunds | 05.0_VENDOR_WORKFLOWS | Refund request system with platform involvement | CRITICAL | Legal liability unclear - who actually processes refunds?
Operations | Chargeback Handling | 01.1_BUSINESS_PLAN | Target chargeback rate <2% | 06.4_FOUNDER_OPERATIONS & 07.1_LEGAL | Vendor responsible for chargebacks, platform only notifies | HIGH | Platform cannot control chargeback rate if vendors handle them
Support | Support SLA Commitment | 03.0_TECHNICAL_OVERVIEW & 06.2_INCIDENT_RESPONSE | No SLA commitments, 70% automation target | 01.3_CONTENT_AND_ENGAGEMENT | 1-on-1 founder support for founding vendors | MEDIUM | Support model contradicts automation-first approach for early vendors
Support | Support Team Staffing | 06.3_ROLES_AND_RESPONSIBILITIES | Support Lead to be contracted after 2 months | 06.2_INCIDENT_RESPONSE | Founder handles support with <1 hour/week target | LOW | Timeline for support scaling unclear
Metrics | Vendor Acquisition Targets | 01.4_MVP_MASTER_PLAN | 200+ vendors by Month 6 | 01.2_ROADMAP_AND_RISK | 500+ vendors by Month 6 | HIGH | 150% difference in success criteria - which is the real target?
Metrics | Initial Vendor Target | 01.3_CONTENT_AND_ENGAGEMENT | 50 founding vendors in 4 weeks | 01.2_ROADMAP_AND_RISK | 50 vendors at soft launch | LOW | Timeline for reaching 50 vendors unclear (4 weeks vs launch date)
Metrics | Transaction Volume Targets | 01.4_MVP_MASTER_PLAN | 300+ transactions/month by Month 6 | 01.2_ROADMAP_AND_RISK | 5,000 customers by Month 6 (no transaction target) | MEDIUM | Success metrics not aligned - customer count vs transaction volume
UX Design | Hero Section CTA Strategy | 02.1_HOMEPAGE_SPECIFICATION & 02.4_PSYCHOLOGY | NO CTA in hero carousel - forced scroll for engagement | Standard conversion best practices | Typical landing pages have hero CTA for immediate conversion | MEDIUM | Unconventional UX strategy - needs A/B testing validation
Design | Typography System | 02-design-system-v3.1-poppins | Poppins as primary branded font (v3.1) | 02.0_DESIGN_SYSTEM | Generic "modern, accessible typography" (no specific font) | LOW | Font choice finalized in v3.1 but not reflected in base design doc
UX Design | Mobile-First vs Desktop Priority | 02.3_PRODUCT_UX_SPECIFICATIONS | Mobile-first design philosophy | 02.2_PAGE_MAPPING | Vendor dashboard features suggest desktop-heavy usage | LOW | Vendor tools may not be optimized for mobile despite mobile-first claim
Geographic Scope | LGA Coverage | 01.1_BUSINESS_PLAN | 12 LGAs in Melbourne for MVP | 08.0_MELBOURNE_SUBURBS_REFERENCE | 31 metropolitan councils mapped | MEDIUM | Unclear which 12 LGAs are priority vs full 31 council coverage
Geographic Scope | Expansion Timeline | 01.1_BUSINESS_PLAN | Expansion to other Australian cities after Melbourne | 01.2_ROADMAP_AND_RISK | Phase 3: Internationalization if revenue >$200k/month | LOW | Expansion strategy jumps from Melbourne to international (skips other AU cities?)
Technical | Development Timeline | 01.0_PROJECT_OVERVIEW | 9-10 weeks, 6 phases, no deadline | 05.1_MVP_SPRINT_PLAN | 4.5 weeks sprint plan with December 1 deadline | CRITICAL | Development timeline completely misaligned (4.5 weeks vs 9-10 weeks)
Technical | Code Quality vs Speed | 01.0_PROJECT_OVERVIEW | 4.5-week aggressive timeline | 05.1_MVP_SPRINT_PLAN |  | HIGH | Philosophy of quality contradicts aggressive sprint timeline
Technical | AI Automation Count | 01.1_BUSINESS_PLAN | 44+ AI automations | 03.0_TECHNICAL_OVERVIEW | Specific automations listed (email, chatbot, queue) - not 44 | MEDIUM | Automation scope unclear - what are the 44 automations?
Financial | Profitability Timeline | 01.1_BUSINESS_PLAN | Pathway to profitability by Month 6 | 01.2_ROADMAP_AND_RISK | Revenue run rate $80,500/month by Month 6 (profitability not mentioned) | MEDIUM | Profitability claim not supported by revenue projections
Financial | Revenue Model Clarity | 01.1_BUSINESS_PLAN | Transaction commissions + Featured slots + potential subscription | 05.0_VENDOR_WORKFLOWS | Free Directory + Basic/Pro tiers with different commission rates | HIGH | Revenue model structure unclear - how do tiers relate to commissions?
Documentation | Multiple Active Versions | Various documents | v1.0, v1.1, v2.0, v2.1, v3.0, v3.1 all present | No master version control document | Unclear which version is current/authoritative | HIGH | Team cannot determine which specifications are current
Documentation | Document Update Status | README | Stage 2.2 complete, design system v3 implemented | Other documents | Multiple documents reference v1.0, v2.0 as current | MEDIUM | Implementation status unclear - what is actually built vs planned?
Documentation | Phase Terminology | 01.0_PROJECT_OVERVIEW | 6 phases (Planning, Infrastructure, Core, Refunds, Support, Polish) | 05.1_MVP_SPRINT_PLAN | Week-based sprints (Week 0-4) | LOW | Inconsistent project structure terminology

## Ambiguities
Category | Issue | Description | Documents_Affected | Required_Decision | Blocker
Technical Specification | Exact Commission Rate | Business plan states 6-8% but no single rate defined | 01.1, 03.0, 03.2 (Stripe integration) | Lock in exact commission percentage (6%, 7%, or 8%) | YES - Stripe Connect configuration requires exact rate
Technical Specification | Featured Slot Duration | $20/month mentioned but slot duration/rotation not specified | 01.1, 03.0, 05.0 | Define slot duration (30 days? calendar month? rolling?) | YES - Queue algorithm needs duration parameter
Business Logic | Directory vs Marketplace Commission | Unclear if Directory listings pay commission or only Marketplace products | 05.0, 03.3 | Clarify: Directory = free listings, Marketplace = commission-based? | YES - Database schema and payment logic depend on this
Business Logic | Tier Commission Differences | Do Basic and Pro tiers pay different commission rates? | 05.0 | Define commission rate per tier (or same for all?) | YES - Payment calculation logic needs this
Operations | Refund Approval Process | Who approves refunds? Vendor? Platform? Automatic? | 05.0, 06.4, 07.1 | Define refund approval workflow and authority | YES - Legal liability and UX flow depend on this
Geographic | Priority LGAs | 12 LGAs mentioned for MVP but 31 councils mapped - which 12? | 01.1, 08.0 | Specify the 12 priority LGAs for MVP launch | MEDIUM - Affects vendor recruitment strategy
Metrics | Success Criteria Authority | Multiple conflicting targets (200 vs 500 vendors, etc.) | 01.2, 01.4 | Establish single source of truth for KPIs | MEDIUM - Affects resource allocation and fundraising
Technical | AI Automation Scope | 44+ automations claimed but only ~10 specified in technical docs | 01.1, 03.0 | List all 44 automations or revise claim | LOW - Marketing claim vs technical reality
UX | Vendor Dashboard Mobile Experience | Mobile-first claimed but vendor tools seem desktop-oriented | 02.2, 02.3 | Define mobile UX for vendor product management | MEDIUM - Affects vendor onboarding friction
Financial | Payout Schedule | Vendor payout timing not specified (daily? weekly? monthly?) | 03.0, 05.0 | Define payout frequency and minimum threshold | YES - Stripe Connect configuration requires this
Legal | Vendor Verification Requirements | ABN required? Business license? Identity verification? | 05.0, 07.1 | Define mandatory vendor verification steps | YES - Onboarding flow and legal compliance depend on this
Product | Product Approval Process | Are products auto-published or require platform approval? | 05.0 | Define product moderation workflow | YES - Affects vendor experience and platform liability

## Decision Matrix
Decision ID | Category | Decision Required | Options | Recommendation | Rationale | Blocks | Priority
D01 | Timeline | Lock in official launch date | Nov 8 / Nov 29 / Dec 1 / No deadline (9-10 weeks) | Remove fixed deadline, adopt 9-10 week quality-first approach | Aligns with Project Overview philosophy; reduces pressure; enables thorough testing | Sprint planning, vendor recruitment timeline, marketing launch | CRITICAL
D02 | Business Model | Define exact commission rate | 6% / 7% / 8% | 7% (middle of stated range) | Competitive vs 15-20% industry standard; allows flexibility; clean percentage | Stripe Connect configuration, financial projections, vendor pricing | CRITICAL
D03 | Business Model | Clarify Directory vs Marketplace commission structure | A) Directory free, Marketplace pays commission ¦ B) Both pay commission ¦ C) Tier-based | Option A: Directory = free listings, Marketplace = 7% commission | Clear value proposition; reduces friction; aligns with hybrid model | Database schema, payment logic, vendor onboarding UX | CRITICAL
D04 | Business Model | Define tier commission differences | A) Same commission for all tiers ¦ B) Lower commission for Pro tier ¦ C) Higher commission for Basic | Option A: Same 7% commission for all marketplace products | Simplicity; transparency; tier value comes from product limits and features | Payment calculation logic, tier value proposition | HIGH
D05 | Operations | Define refund processing responsibility | A) Vendors process directly ¦ B) Platform processes ¦ C) Platform facilitates, vendor approves | Option C: Platform facilitates request, vendor approves/declines, platform notifies | Balances vendor control with platform oversight; reduces liability; maintains trust | Refund workflow UX, legal liability, Stripe integration | CRITICAL
D06 | Financial | Define vendor payout schedule | Daily / Weekly / Bi-weekly / Monthly | Weekly payouts with $50 minimum threshold | Balances cash flow for vendors with operational efficiency; industry standard | Stripe Connect configuration, vendor expectations | HIGH
D07 | Legal | Define vendor verification requirements | A) ABN only ¦ B) ABN + ID ¦ C) ABN + ID + Business license ¦ D) No verification | Option B: ABN + Government-issued ID verification | Balances trust/compliance with onboarding friction; standard for AU marketplaces | Onboarding flow, legal compliance, fraud prevention | HIGH
D08 | Product | Define product approval process | A) Auto-publish ¦ B) Manual review ¦ C) Auto-publish with post-moderation | Option C: Auto-publish with AI flagging + post-moderation | Reduces vendor friction; enables automation; maintains quality control | Product upload UX, moderation workflow, platform liability | HIGH
D09 | Metrics | Lock in Month 6 vendor target | 200 vendors / 500 vendors | 500 vendors (from Roadmap doc) | More ambitious; aligns with revenue projections; realistic for 6-month timeline | Resource allocation, fundraising pitch, success criteria | MEDIUM
D10 | Geographic | Specify 12 priority LGAs for MVP | Select from 31 mapped Melbourne councils | Focus on inner/middle ring: Melbourne, Port Phillip, Yarra, Stonnington, Boroondara, Moreland, Darebin, Maribyrnong, Moonee Valley, Banyule, Whitehorse, Monash | Higher density; younger demographics; better vendor/customer concentration | Vendor recruitment strategy, marketing focus | MEDIUM
D11 | Technical | Define featured slot duration | 30 rolling days / Calendar month / 4 weeks | 30 rolling days from purchase | Fair for all vendors; simple to calculate; aligns with $20/month pricing | Queue algorithm, Stripe subscription logic | HIGH
D12 | UX | Define mobile UX for vendor dashboard | A) Full mobile optimization ¦ B) Desktop-first with mobile view ¦ C) Mobile app required | Option A: Full mobile optimization with responsive design | Aligns with mobile-first philosophy; reduces vendor friction; no app development needed | Vendor dashboard design, product management UX | MEDIUM

## Document Mapping
Current Document | Version | New Location | Section | Status | Notes
01.0_PROJECT_OVERVIEW | v1.1 | 01_BUSINESS_STRATEGY_v3.1.md | Development Philosophy | Consolidate | Extract quality-first principles
01.1_BUSINESS_PLAN | v2.0 | 01_BUSINESS_STRATEGY_v3.1.md | Business Model & Revenue | Consolidate | Resolve commission rate ambiguity
01.2_ROADMAP_AND_RISK | v2.0 | 01_BUSINESS_STRATEGY_v3.1.md | Roadmap & Risk Mitigation | Consolidate | Use 500 vendor target
01.3_CONTENT_AND_ENGAGEMENT | v2.0 | 01_BUSINESS_STRATEGY_v3.1.md | Go-to-Market Strategy | Consolidate | Keep vendor recruitment tactics
01.4_MVP_MASTER_PLAN_SUMMARY | v1.1 | 01_BUSINESS_STRATEGY_v3.1.md | MVP Overview | Consolidate | Resolve launch date conflict
02.0_DESIGN_SYSTEM | v3.0 | 02_PRODUCT_UX_v3.1.md | Design System | Consolidate | Superseded by v3.1
02-design-system-v3.1-poppins | v3.1 | 02_PRODUCT_UX_v3.1.md | Design System | Primary Source | Current design system
02.1_HOMEPAGE_SPECIFICATION | v2.0 | 02_PRODUCT_UX_v3.1.md | Homepage | Consolidate | Merge with v2.1
02-homepage-complete-specs-v2.1-evolved | v2.1 | 02_PRODUCT_UX_v3.1.md | Homepage | Primary Source | Latest homepage spec
02.2_PAGE_MAPPING_AND_LAYOUTS | v2.0 | 02_PRODUCT_UX_v3.1.md | Page Mapping | Consolidate | 13 core pages
02.3_PRODUCT_UX_SPECIFICATIONS | v3.0 | 02_PRODUCT_UX_v3.1.md | UX Specifications | Consolidate | Mobile-first principles
02.4_PSYCHOLOGY_AND_IMMERSIVE_UX | v1.0 | 02_PRODUCT_UX_v3.1.md | UX Psychology | Consolidate | Forced scroll strategy
02-ux-interactivity-layer-v1.0 | v1.0 | 02_PRODUCT_UX_v3.1.md | Interactivity | Consolidate | Scroll animations, modals
image-specifications | v1.0 | 02_PRODUCT_UX_v3.1.md | Image Specs | Consolidate | Grayscale + accent overlays
README | Current | 09_IMPLEMENTATION_STATUS.md | Build Status | Migrate | Stage 2.2 complete
03.0_TECHNICAL_OVERVIEW | v3.0 | 03_TECHNICAL_ARCHITECTURE_v3.1.md | Overview | Consolidate | Tech stack & architecture
03.1_VISUAL_DIAGRAMS | v1.0 | 03_TECHNICAL_ARCHITECTURE_v3.1.md | Diagrams | Consolidate | ERD, dataflow, payment flow
03.2_INTEGRATIONS_AND_TOOLS | v2.0 | 03_TECHNICAL_ARCHITECTURE_v3.1.md | Integrations | Consolidate | Stripe, Resend, Supabase, S3
03.3_SCHEMA_REFERENCE | v1.0 | 03_TECHNICAL_ARCHITECTURE_v3.1.md | Database Schema | Consolidate | Directory/Marketplace tables
05.0_VENDOR_WORKFLOWS | v2.1 | 05_IMPLEMENTATION_PLAN_v3.1.md | Workflows | Consolidate | Directory + Marketplace flows
05.1_MVP_SPRINT_PLAN | v1.0 | 05_IMPLEMENTATION_PLAN_v3.1.md | Sprint Plan | Revise | Align with 9-10 week timeline
06.0_DEVELOPMENT_PLAN | v2.0 | 06_OPERATIONS_v3.1.md | Development Process | Consolidate | 12-week plan
06.1_DEPLOYMENT_PROCEDURES | v1.0 | 06_OPERATIONS_v3.1.md | Deployment | Consolidate | Change management
06.2_INCIDENT_RESPONSE_RUNBOOKS | v2.0 | 06_OPERATIONS_v3.1.md | Incident Response | Consolidate | Runbooks & monitoring
06.3_ROLES_AND_RESPONSIBILITIES | v1.0 | 06_OPERATIONS_v3.1.md | Roles | Consolidate | Team structure
06.4_FOUNDER_OPERATIONS | v1.1 | 06_OPERATIONS_v3.1.md | Founder Playbook | Consolidate | Decision matrix
07.0_QA_AND_TESTING_STRATEGY | v1.0 | 07_COMPLIANCE_QA_v3.1.md | QA Strategy | Consolidate | Testing approach
07.1_LEGAL_COMPLIANCE_AND_DATA | v3.0 | 07_COMPLIANCE_QA_v3.1.md | Legal & Compliance | Consolidate | Vendor agreements, privacy
08.0_MELBOURNE_SUBURBS_REFERENCE | v1.0 | 08_MELBOURNE_SUBURBS_REFERENCE.md | All | Keep As-Is | Add priority 12 LGAs

## Implementation Roadmap
Phase | Duration | Tasks | Deliverable | Owner | Dependencies | Success Criteria
Phase 0: Decision Lock-In | 1-2 days | Review Decision Matrix (D01-D12), Make final decisions on all CRITICAL items, Document in 00_MASTER_DECISIONS.md | 00_MASTER_DECISIONS.md with all 12 decisions locked | Founder + Product Lead | None | All CRITICAL and HIGH priority decisions finalized
Phase 1: Document Consolidation | 3-5 days | Consolidate 29 documents into 9 master documents, Resolve contradictions using Master Decisions, Remove redundancy, Update all version numbers to v3.1 | 9 consolidated v3.1 documents | Technical Writer / Product Lead | Phase 0 complete | Zero contradictions, single source of truth for each topic
Phase 2: Technical Specification | 2-3 days | Update database schema with locked decisions, Configure Stripe Connect with exact commission rate, Define API contracts with payout schedule, Update RLS policies | Updated 03_TECHNICAL_ARCHITECTURE_v3.1.md with implementation-ready specs | Lead Developer | Phase 1 complete | All technical ambiguities resolved, ready for development
Phase 3: Sprint Planning | 1-2 days | Revise sprint plan based on locked timeline, Align feature prioritization with Master Decisions, Update development phases, Create sprint backlog | Updated 05_IMPLEMENTATION_PLAN_v3.1.md with realistic timeline | Product Lead + Lead Developer | Phase 2 complete | Sprint plan aligns with quality-first philosophy
Phase 4: Workflow Documentation | 2-3 days | Document Directory vs Marketplace workflows, Create vendor onboarding flow with verification, Define refund approval process, Update customer journey maps | Updated 05_IMPLEMENTATION_PLAN_v3.1.md with clear workflows | Product Lead | Phase 3 complete | All user flows documented with no ambiguity
Phase 5: Legal & Compliance | 2-3 days | Update vendor agreements with refund policy, Finalize T&Cs with commission structure, Document verification requirements, Update privacy policy | Updated 07_COMPLIANCE_QA_v3.1.md with legal-ready documents | Founder + Legal Advisor | Phase 4 complete | Legal documents ready for launch
Phase 6: Version Control Setup | 1 day | Archive old versions (v1.0-v3.0), Establish version control process, Create change log template, Set up document review schedule | Version control system + archived old docs | Product Lead | Phase 5 complete | Clear process for future document updates
Phase 7: Team Alignment | 1 day | Present consolidated docs to team, Review Master Decisions, Align on timeline and priorities, Q&A session | Team alignment meeting + sign-off | Founder | Phase 6 complete | All team members understand and agree on direction
Phase 8: Development Kickoff | Ongoing | Begin development based on consolidated specs, Track progress in 09_IMPLEMENTATION_STATUS.md, Weekly doc review meetings, Update docs as needed | Active development with living documentation | Entire Team | Phase 7 complete | Development proceeds without spec ambiguity